## agile-sprint-planni
Agile - Sprint Planning For Enterprise Web Software Development
Group : Fanstatic Four
Sprint 5(Deliveries and close project))
Name | Progress | Days | Timeline - Start | Timeline - End | Priority | Task owner | Task status | Comment | Estimated Effort(h/day)
Collect requirement | 100% | 2 | 2022-04-03 | 2022-04-04 | High | Khoant | Done | In time | 5
Analysis requirement | 100% | 2 | 2022-04-03 | 2022-04-04 | High | Khoant | Done | In time | 5
Planing | 100% | 2 | 2022-04-03 | 2022-04-04 | Low | Khoant | Done | In time | 4
Writing document test | 100% | 7 | 2022-04-05 | 2022-04-11 | Medium | Huytn | Done | Late | 4
Final testing | 100% | 4 | 2022-04-11 | 2022-04-14 | Medium | Dud, Khoant, Huynk, Huytn | Done | Late | 6
Report document | 100% | 9 | 2022-04-09 | 2022-04-17 | High | Dud, Khoant, Huynk, Huytn | Done | Late | 6
Preview | 100% | 1 | 2022-04-17 | 2022-04-17 | Medium | Khoant | Done | Late | 4
Presentation | 100% | 4 | 2022-04-15 | 2022-04-18 | Medium | Dud, Khoant, Huynk, Huytn | Done | Late | 4
| 100% |  | 2022-04-03 | 2022-04-18 |  |  |  |  | 38
Sprint 4 (Implement-3)
Name | Progress | Days | Timeline - Start | Timeline - End | Priority | Task owner | Task status | Comment | Estimated Effort(h/day)
Collect requirement | 100% | 2 | 2022-03-25 | 2022-03-26 | High | Khoant | Done | In time | 4
Analysis requirement | 100% | 2 | 2022-03-25 | 2022-03-26 | High | Khoant | Done | In time | 4
Planing | 0% | 2 | 2022-03-25 | 2022-03-26 | Medium | Khoant | Scope out | In time | 4
Create UI for MyIdeas | 100% | 3 | 2022-03-27 | 2022-03-29 | High | Huytn, Huynk | Done | Late | 6
Create UI for Staff | 100% | 4 | 2022-03-29 | 2022-04-01 | High | Huytn, Huynk | Done | Late | 6
Create CRUD and data for MyIdeas | 100% | 3 | 2022-03-27 | 2022-03-29 | High | Dud, Khoant | Done | Late | 6
Create CRUD and data for Staff | 100% | 5 | 2022-03-29 | 2022-04-02 | High | Dud, Khoant | Done | Late | 6
Preview | 100% | 2 | 2022-04-02 | 2022-04-03 | Medium | Khoant | Done | In time | 2
Testing | 100% | 2 | 2022-04-02 | 2022-04-03 | Medium | Huytn | Done | In time | 2
| 89% |  | 2022-03-25 | 2022-04-03 |  |  |  |  | 40
Sprint 3(Implement-2)
Name | Progress | Days | Timeline - Start | Timeline - End | Priority | Task owner | Task status | Comment | Estimated Effort(h/day)
Collect requirement | 100% | 2 | 2022-03-18 | 2022-03-19 | High | Khoant | Done | In time | 4
Analysis requirement | 100% | 2 | 2022-02-18 | 2022-02-19 | High | Khoant | Done | In time | 5
Planing | 100% | 2 | 2022-03-18 | 2022-03-19 | Medium | Khoant | Done | In time | 4
Create UI for Categories | 100% | 3 | 2022-03-20 | 2022-03-22 | High | Huytn, Huynk | Done | In time | 6
Create CRUD and data for Categories | 100% | 3 | 2022-03-20 | 2022-03-22 | High | Dud, Khoant | Done | In time | 6
Create UI for Submission | 100% | 3 | 2022-03-20 | 2022-03-22 | High | Huytn, Huynk | Done | Soon | 6
Create CRUD and data for Submission | 100% | 3 | 2022-03-20 | 2022-03-22 | High | Dud, Khoant | Done | Late | 6
Preview | 100% | 2 | 2022-03-23 | 2022-03-24 | Medium | Khoant | Done | In time | 2
Testing | 0% | 2 | 2022-03-23 | 2022-03-24 | Medium | Huytn | Scope out | In time | 3
| 89% |  | 2022-02-18 | 2022-03-24 |  |  |  |  | 42
Sprint 2(Implement-1)
Name | Progress | Days | Timeline - Start | Timeline - End | Priority | Task owner | Task status | Comment | Estimated Effort(h/day)
Collect requirement | 100% | 2 | 2022-03-02 | 2022-03-03 | Medium | Khoant | Done | In time | 4
Analysis requirement | 100% | 2 | 2022-03-02 | 2022-03-03 | Medium | Khoant | Done | In time | 5
Planing | 0% | 2 | 2022-03-02 | 2022-03-03 | Medium | Khoant | Scope out | In time | 4
Design wireframe | 100% | 2 | 2022-03-03 | 2022-03-04 | High | Huytn, Du, Khoant | Done | Soon | 4
Design database | 100% | 2 | 2022-03-03 | 2022-03-04 | High | Khoant | Done | Soon | 4
Design usecase | 100% | 3 | 2022-03-03 | 2022-03-05 | High | Huytn | Done | In time | 4
Design function | 100% | 3 | 2022-03-03 | 2022-03-05 | High | Dud, Khoant | Done | In time | 8
Create UI for Login | 100% | 5 | 2022-03-05 | 2022-03-09 | High | Huynk, Huytn | Done | Late | 3
Create function for Login | 100% | 5 | 2022-03-05 | 2022-03-09 | High | Huytn | Done | Late | 5
Create UI for Dashboard | 100% | 3 | 2022-03-09 | 2022-03-11 | High | Huynk, Huytn | Done | Soon | 6
Create UI for Profile | 100% | 4 | 2022-03-09 | 2022-03-12 | High | Huynk, Huytn | Done | Late | 3
Create CRUD and data for Profile | 100% | 5 | 2022-03-09 | 2022-03-13 | High | Dud, Khoant | Done | In time | 5
Create UI for Ideas | 100% | 6 | 2022-03-09 | 2022-03-14 | High | Huynk, Huytn | Done | Soon | 6
Create CRUD and data for Ideas | 100% | 3 | 2022-03-11 | 2022-03-13 | High | Dud, Khoant | Done | In time | 4
Create UI for Department | 100% | 4 | 2022-03-12 | 2022-03-15 | High | Huynk, Huytn | Done | Late | 6
Create CRUD and data for Department | 100% | 5 | 2022-03-12 | 2022-03-16 | High | Dud, Khoant | Done | Soon | 4
Preview | 0% | 2 | 2022-03-16 | 2022-03-17 | Medium | Khoant | Scope out | In time | 4
Testing | 100% | 2 | 2022-03-16 | 2022-03-17 | Medium | Huytn | Done | In time | 3
| 89% |  | 2022-03-02 | 2022-03-17 |  |  |  |  | 82
Sprint 1(Start Project )
Name | Progress | Days | Timeline - Start | Timeline - End | Priority | Task owner | Task status | Comment | Estimated Effort(h/day)
Collect requirement | 100% | 3 | 2022-02-13 | 2022-02-15 | High | Khoant | Done | In time | 4
Analysis requirement | 100% | 3 | 2022-02-13 | 2022-02-15 | High | Khoant | Done | In time | 5
Planing | 100% | 2 | 2022-02-15 | 2022-02-16 | High | Khoant | Done | In time | 3
Work divide | 100% | 2 | 2022-02-15 | 2022-02-16 | Medium | Khoant | Done | Soon | 2
Learning PHP | 100% | 15 | 2022-02-16 | 2022-03-02 | High | Dud, Khoant, Huynk, Huytn | Done | Late | 8
Learning about MVC | 100% | 15 | 2022-02-16 | 2022-03-02 | High | Dud, Khoant, Huynk, Huytn | Done | Late | 8
Learning about MySQL | 100% | 15 | 2022-02-16 | 2022-03-02 | High | Dud, Khoant, Huynk, Huytn | Done | Late | 8
IDE | 100% | 2 | 2022-02-16 | 2022-02-17 | Medium | Dud, Khoant, Huynk, Huytn | Done | Soon | 4
Gantt chart | 100% | 2 | 2022-03-16 | 2022-03-17 | Low | Huytn | Done | In time | 2
Searching for necessary tool and apps | 100% | 4 | 2022-02-15 | 2022-02-18 | High | Dud, Khoant, Huynk, Huytn | Done | In time | 8
Preview | 0% | 2 | 2022-03-01 | 2022-03-02 | Medium | Khoant | Scope out | In time | 4
Testing | 100% | 2 | 2022-03-01 | 2022-03-02 | Medium | Huytn | Done | In time | 3
| 92% |  | 2022-02-13 | 2022-03-17 |  |  |  |  | 59